# TRANSFORMING AGRICULTURE THROUGH DIVERSIFICATION AND ENTREPRENEURSHIP (TRADE) PROGRAMME

Rumphi Mhunju Cluster - Terms of Reference for Business Coaching Services for Mhuju Beef FBOs

To

IMPLEMENT PROJECTS UNDER TRADE PROGRAMME

Ref No: [TRADE Programme 2024/ 2025 Procurement Plan 1.1.1.6]

September 2024

- BACKGROUND OF TRADE PROGRAMME (see www.tradeprogramme.org for more details)

TRADE Programme is a six-year Programme which was financed as a successor Programme of Rural Livelihoods and Economic Enhancement Programme (RLEEP). The Programme is being co-funded by International Fund for Agricultural Development (IFAD) and OPEC Fund for International Development (OFID). The goal of TRADE is to improve sustainable livelihoods of rural people in Malawi. The development objective is “Increased value chain commercialization and resilience of rural poor and smallholder producers”. The development objective is being achieved through a holistic approach to addressing the agriculture commercialization challenge (building on RLEEP and informed by IFAD’s Engagement in Pro-poor Value Chain Development). TRADE will seek to:

- Increase production and productivity by smallholder farmers,

- Functionally upgrade smallholder farmers and the rural poor to undertake new functions such as processing, storage, packaging to capture more value,

- Improving horizontal linkages by strengthening the capacities of cooperatives to provide market access functions to smallholder farmers

- Improve vertical linkages between stakeholders at different functional levels of the commodity chain, including private sector. TRADE is also supporting rural entrepreneurs, focusing on youths and women to develop and sustain their agribusiness enterprise opportunities and ensuring that commodities are nutrition sensitive.

The Programme aims to achieve its outcomes through the delivery of the following outputs:

- Creation of win-win partnerships between producers, private and public actors.

- Enhancement of business skills among smallholder farmers

- Strengthening Farmer Based Organizations

- Linking smallholder farmers to rural financial services

- Enhancing crop and livestock production skills among smallholder farmers.

- Promotion of climate smart agriculture technologies / practices

- Increased policy Influencing capacity and formal business arrangements

- Construction of Commodity support infrastructure.

TRADE Programme’s investments are market driven, facilitation oriented and risk buy-off.  These approaches culminate into horizontal and vertical linkages of smallholders farmers to enhance their productivity and value chain upgrading efforts. These however require the presence of vibrant Farmer Business Organizations (FBOs) filled and managed by farmers with relevant agribusiness skills and orientation and capable of accelerating smallholder commercialization. It is on this basis that TRADE Programme intends to engage business coaches who will provide hands-on-ground agribusiness coaching and mentorship services to FBOs to address various agribusiness constraints in their respective FBOs in order to promote the commercialization of the target value chains.

- Background to the business coaching assignment

In Malawi, 80% of farmers produce most of the food for domestic consumption and surplus for the market. Smallholder producers are facing challenges to commercialize their agriculture and effectively participate in input and output markets. There are a number of barriers affecting the performance of FBO which include the following:

- These include low production and productivity,

- Weak and unsustainable partnerships with private sector,

- Lack of business skills to operate as commercial enterprises,

- Weak FBO management skills which result in inability of FBOs to provide key services to their respective members such as access to inputs, finance and market opportunities,

- Low value addition efforts due to limited access to finance and poor cooperative management skills and governance style.

In addition, low participation of women and youths in these FBOs debar the involvement of critical labour mass capable of driving the commercialization agenda.

Thus TRADE Programme intends to engage business coaches to work with FBOs to provide hands on training, mentorship and coaching services to them. Business coaching, is a process of providing guidance and support to develop FBO skills, knowledge and capacities in relation to their agriculture businesses. Focus areas of Business Coaching for the targeted FBOs will be cultivating entrepreneurial mind set, development of business skills and FBO management capacity and understanding the benefits, pathways and costs of effectively engaging within the business-oriented FBOs.

The business coaches (BCs) will be expected to first identify and assess the FBOs that are willing and committed to the process of commercialization. The engaged market oriented individual BCs will facilitate this process on the ground by taking, preferably, FBO leaders and, and where applicable, FBO members through different stages of organizational assessment and capacity enhancement so that they are able to critically examine their FBO business objectives, strategies and overall enterprise management. They will also support FBO leaders and members to drive organizational change management processes and develop strategic business partnerships as well as review existing or develop new business plans. As such, this will build capacity for farmers and Farmer Organizations (FOs) to engage in commercial partnerships. Through these interventions, it is expected that the FBOs will be empowered and have a better understanding of their businesses.

Business coaching services will be provided regularly by skilled, knowledgeable and experienced BCs through practical training, milestone-based engagement with private sector and other input providers, mentorship and where necessary incubation. FBOs such as cooperatives and milk bulking groups (MBGs) among others, need support in designing, implementing, monitoring and evaluating their business plans as well as developing their skills in active engagement with other value chain players that provide an output and input market. The business coaches will be hired with the role of coaching and mentoring the FBOs through dedicated assistance based on the specific capacity gaps identified thorough in-depth FBO capacity needs assessment already conducted by TRADE Programme to be confirmed by the BCs themselves during their first steps of engagement.

Initially TRADE support will target FBOs in the 11 RLEEP districts. FBOs that will need matching grants but do not meet eligibility criteria for ACIF will be strengthened to meet basic eligibility criteria and/or supported through FARMSE or other financial institutions to access financial resources for critical investments in their business operations through the services of the BCs. Business Coaches will ensure participation of women and youth in FBOs, including leadership positions. This means youth or women-based FBOs will also be targeted for the coaching and mentoring services. Under the support of the BC services, TRADE will also ensure that the FBOs have strengthen governance aspects related to leadership, accountability, transparency and inclusive participation in decision making.

The BCs will be expected to link with existing NGOs, private sector players and Government Subject Matter Specialists to implement the assignment to bring synergies and harmonization of related interventions and to avoid duplication.

3.0. Objectives of the BC services

3.1. Overall objectives of the BC services

Overall the business coaches will be tasked to facilitate win-win marketing arrangements with traders, processors and/or major off-takers through improved communication and negotiation skills, market-based production programming and joint marketing. In this process, the business coaches will be expected to actively hand-hold the farmers/cooperatives up to the stage of signing supply contracts that ensure a fair distribution of the profits and enhanced trust between the different parties, which is essential for sustainability.

3.2. Specific Objectives of the BC Services

Specifically, the services of the BCs will be expected to achieve the following:

    - Strengthening overall business operational and managerial skills;

    - Promoting access to inputs and finance by the FBOs through support with skills and competencies in developing competitive grant proposals including supporting them to access ACIF small and large grants from TRADE Programme as key 4P partners

    - Improving services to their members in output and input market access.

    - Product bulking for joint marketing so that they are able to increased volume of business, reduce operating costs, increase profitability and attract new members to increase number of farmers participating;

    - Creation of commercial partnerships with private companies in 4P model or linkages to large commodity traders; and

    - Increasing capital (shares) and joint investments to increase profits.

    - Promote profitable equipment hiring schemes where applicable

- Scope of work

Working very closely with the TRADE Programme staff particularly the Commodity Specialists and the Agribusiness and Value Chain Specialist, business coach will be assigned to a cluster and FBOs of their choice which should be indicated in their application letter, preferably, located in the same District and /or Extension Planning Area (EPA) for a period of between 6 to 12 months depending on the level of maturity of the FBO and the magnitude of assigned deliverables. Notwithstanding the need for flexibility on each FBO, coaching is generally expected to follow three steps as follows:

Step 1 : The Business Coaches will first carry out a rapid capacity assessment of the FBOs to and come up with a robust coaching plan. The rapid assessment will re-assess capacity gaps and potential based on current challenges and opportunities. The BC rapid analysis will also reaffirm commitment of the groups to commodity commercialization. This assessment will also include literacy levels, technical and managerial capabilities, and diversity of businesses in order to define different interventions and priorities for each FBO and avoid a “one size fits all” coaching approach. The Business Coaches will also allow the members to critically examine their FBO business objectives, strategies and management capacity.

Step 2: After the rapid assessment, the Business Coaches shall undertake participatory processes to formulate each FBO’s vision and develop an improved and more feasible business model as well as financing strategies and take concrete steps towards planning and managing change within their organizations. The concrete steps will be part of the coaching plan based on the gaps identified. This shall be followed by the implementation of actions with integrated reflection and refinement of events or moments. The organisation coaching plan will also include indicators to track and evaluate progress in the organisational transformation.

Step 3: Regular coaching and hand holding will support FBOs’ leaders and members to drive organisational change management processes and develop strategic business partnerships. As such, this will build capacity of farmers and Farmer Organisations (FOs) to engage in commercial partnerships. Under step 3, specific interventions will be aimed at attaining the following deliverables:

  - Farmer Business Organizations strengthened: The objective of this activity is to enable FBOs to become commercial entities to effectively support their members. The support will include both training, hands on coaching and mentoring provided by the specialized BCs to strengthen overall business performance and managerial skills; improve services to their members such as bulk buying of inputs, product bulking for joint marketing, creation of commercial partnerships with private companies in 4P model or linkages to large commodity traders and increasing capital (shares) and joint investments to increase profits.

  - Relationships in the 4P model facilitated: The 4P or similar partnerships established with the investment support from the Agriculture Commercialization and Innovation Fund (ACIF), will require intensive coaching. Even before the partnerships are formed the support of an experienced BCs is required to facilitate discussions, to guide the joint business planning and to clearly stipulate each of the partners’ roles and responsibilities in the 4P. The Business Coach will also support the 4P implementation process, to achieve the key milestones and to facilitate the dialogue between the 4P partners. The level of business coaching of 4Ps depends entirely on the development level and experience of the partners involved in the 4P.

  - Informal and formal FBOs Commercialization Enhanced: Coaching of the FBOs will take place regularly by a specialized business coach. In order to fully benefit their members, cooperatives need support in implementing their business plan. Business Coaches will be hired with a role of a coach or mentor; they will support the Farmer Clubs, Youth clubs, Farmer Organizations and Cooperatives through dedicated assistance based on the specific challenges they meet, and along the different stages of the commodity. The Business Coach will facilitate business plan development of the group through visioning and clear goal setting.

  - Marketing arrangements within the value chain facilitated: Business coaches will be tasked to facilitate marketing arrangements with traders, processors and/or major off-takers through improved communication and negotiation skills, market-based production programming and joint marketing. In this process, the business coaches are expected to actively hand-hold the farmers/cooperatives up to the stage of signing supply contracts that ensure a fair distribution of the profits and enhanced trust between the different parties, which is essential for sustainability. Where needed, TRADE will facilitate and support the drafting of model constitutions and by-laws for different type of business groups, which can be adapted to suit specific situations. This will directly link to 4P facilitation activities under sub-component 1.1 (Productivity enhancement and commodity Commercialization) and (2.2 (Improve regulatory framework for contracts enforcement).

  - FBO eligibility for ACIF Enhanced: Together with commodity specialists and service providers, BCs will mobilize and support smallholder producer organizations and resource constrained farmer agribusiness groups to enhance their eligibility for ACIF. Consequently, this will help in providing linkages of such groups to community based financial service providers, such as VSLA and SACCOs to access seasonal loans through FARMSE to increase their farming investments. This will enable the targeted FBOs to increase their farm productivity, produce surpluses and participate in value chain commercialization in sustainable manner.

The BC assignment will focus on coaching FBOs for the following list of FBOs and their respective locations including gaps which were identified during FBO assessments conducted by TRADE PMU. The gaps assessment exercise focused on capacity issues of the FBOs in relation to leadership and governance, services provided to FBO membership, financial management, membership and share capital growth, ability to access financing, ability to attract members to aggregate their produce with the FBOs for collective marketing as outlined below:

:

5.0. Summary description of each FBO

5.1. Mwenembe Beef Cooperative (Ntchenachena EPA)

Governance: Mwenembe Beef Cooperative was registered in 2023 under the Cooperative Societies Act. During the training and registration processes the Cooperative developed by-laws which provides a legal framework of the cooperative as well as forming part of the operational guidelines. They have so far only held one general assembly where they fine-tuned the by-laws. The by-laws allow leaders to hold positions for a maximum of two fixed terms of 2 years each. The leadership positions are generally dominated by male persons. There is one woman and one youth who hold non-decision-making positions.

Services: The Cooperative is a beef cooperative. Currently there are no initiatives on aggregation and / or collective marketing arrangements. Individual beef farmers are still selling only live animals independently, which is an area that needs to be improved. There is high potential that the cooperative may provide market information to its members as well as enhancing a collective bargaining power to access competitive markers. Sush services are currently non-existent. However the cooperative has so far been able to support some of its paid members to access drugs and veterinary services including artificial insemination (AI) services at a very minimal scale, leaving a big room for improvement.

Financial Management: The Cooperative is relatively new as it has been recently registered. They currently do not have budgets or cash flow documents. They have not so far developed financial reports. They do not have internal control documents and have not been audited. They keep basic records, especially on membership payments and share buying. They also keep records of expenditure, although there was no evidence of expenditure supporting documents such as receipts, leading to inability to track financial transactions.

Membership/ Shares: The Cooperative has 71 members (Male 45, Female 26, Youth 13, 0PWD). Only 26 mebers have been able to buy shares. The price of one share is MWK 80,000.  Members are also required to subscribe with an annual membership fee of MWK 5,000 per member.

Aggregated volumes: At this stage the Cooperative do not practice collective marketing. A few members reported to have been able to supply beef at Phwezi Technical College, Phwezi Secondary School, Livingstonia University, Rumphi TTC, Rumphi Secondary School and Rumphi Hospital. However, the individuals selling beef to these institutions do not have bound contracts with them. This situation exposes them to market volatility without fixed process, a situation which may lead to abrupt loss of business opportunity and financial losses in some cases.

Access to finance: Currently the Cooperative does not have a business plan. They have not been able to access in the form of financing, neither a grant nor loan, because it has just been registered and did not qualify to apply for funding including ACIF matching grant under TRADE Programme.

5.2. Mumwaka Beef Cooperative (Mwazisi EPA)

Governance: Mwenembe Beef Cooperative was registered in 2023 under the Cooperative Societies Act. During the training and registration processes they developed by-laws which provides a legal framework of the cooperative as well as forming part of the operational guidelines. They have so far only held one general assembly deliberating issues that mainly related to planning and budgeting. The by-laws allow leaders to hold positions for a maximum of two fixed terms of three years each. The leadership positions are generally dominated by male persons. There are two women in the decision-making positions (One is Secretary, and the other is an executive member). No youth or people with disabilities hold any leadership positions.

Services: The cooperative has not offered any services to its members so far since it has just been registered. They have plans to start procuring inputs such as veterinary drugs to provide to its members on loan. They also have plans to organize themselves and construct an abattoir at which its members could slaughter their animals and sale the beef to competitive markets. They also have plans to start processing beef into other products such as sausages and mincemeat.

Financial Management: The Cooperative is relatively new as it has been recently registered. They currently do not have budgets or cash flow documents. They have not so far developed financial reports. They do not have internal control documents and have not been audited. They keep basic records, especially on membership payments and share buying. They also keep records of expenditure, although there was no evidence of expenditure supporting documents such as receipts, leading to inability to track financial transactions.

Membership/ Shares: The Cooperative has 66 members (Male 47, Female 19, of which 13 are Youth, 0PWD). Thirty (30) members have bought shares. The price of one share is MWK 100,000 but in their by-law is a requirement that members can buy shares in instalments.  Members are also required to subscribe with an annual membership fee of MWK 5,000 per member.

Aggregated volumes: They so far have not started aggregating but some of its members independently sale beef to various institutions in Rumphi.

Access to finance: Currently the Cooperative does not have a business plan. They have not been able to access in form of financing, neither a grant nor loan, because it has just been registered and did not qualify to apply for funding including ACIF matching grant under TRADE Programme.

5.3. Mhuju Livestock Cooperative (Mhuju EPA)

Governance: Mhuju Beef Cooperative was registered in 2023 under the Cooperative Societies Act but have not yet received their registration certificate. They have by-laws in place which provides a legal framework of the cooperative as well as forming part of the operational guidelines. They have so far only held one general assembly deliberating issues that mainly related to agree about the price of the share and other pertinent regulations. The by-laws allow leaders to hold positions for a maximum of three fixed terms of one year each. The leadership positions are generally dominated by male persons. There are only two women in the leadership positions and two youth as well.

Services: The cooperative has been offering dipping services for its members at a fee. They also intend to support its members by engaging technical experts to build capacity of its members in beef fattening. They have a partially operational drug revolving scheme which some of its members are benefiting from, although in most cases some of the important drugs are unavailable.

Financial Management: Mhuju Cooperative have a bank account with FDH Bank. They currently do not have budgets or cash flow documents. They have not so far developed financial reports. They do not have internal control documents and have not been audited. They keep basic records, especially on membership payments and share buying as well as dipping fees. They also keep records of expenditure, although there was no evidence of expenditure supporting documents such as receipts, leading to inability to track financial transactions.

Membership/ Shares: The Cooperative has 55 members (Male 35, Female 20, of which 10 are Youth, 0PWD). No member has yet bought any shares. Members are required to subscribe with an annual membership fee of MWK 10,000 per member.

Aggregated volumes: They so far have not started aggregating but some of its members independently sale beef to various institutions in Rumphi.

Access to finance: Currently the Cooperative does not have a business plan. They have not been able to access any form of financing, neither a grant nor loan. At some point AGCOM approached them to discuss possibilities of its members obtaining matching grants to buy animals but this did not materialize because they were then not registered as a formal farmer organization. There is a high potential that they can apply for ACIF and other available grant opportunities.

5.4. Bolero Beef Cooperative (Bolero EPA)

Governance: Bolero Beef Cooperative was registered in 2023 under the Cooperative Societies Act. They have by-laws in place which provide a legal framework of the cooperative as well as forming part of the operational guidelines. Their by-laws allow leaders to hold positions for a maximum of three fixed terms of one year each. The leadership positions are generally dominated by male persons. There is only one woman in the leadership positions and two youth as well.

Services: Bolero Beef Cooperative offers extension services to its members, especially feed making services. The Cooperative also supports its members to access livestock drugs through a loan scheme they are implementing with Muliko Enterprises.

Financial Management: Bolero Beef Cooperative do not have budgets or cash flow documents. They have not so far developed financial reports. They do not have internal control documents and have not been audited. They keep basic records, especially on membership payments and share buying as well as membership fees. They also keep records of expenditure, although there was no evidence of expenditure supporting documents such as receipts, leading to inability to track financial transactions.

Membership/ Shares: The Cooperative has 43 members (Male 25, Female 18, of which 7 are Youth, 0 PWD). Out of 43 members, 16 are the only ones who bought a full share. The cost of the share is MWK 90,000. Members are required to subscribe with an annual membership fee of MWK 10,000 per member.

Aggregated volumes: They so far have not started aggregating but some of its members independently sale beef to various institutions in Rumphi.

Access to finance: Currently the Cooperative does not have a business plan. They have not been able to access any form of financing, neither a grant nor loan. There is a high potential that they can apply for ACIF and other available grant opportunities.

5.5. Summary of major challenges identified within the FBOs

In overall most of the FBOs are experiencing similar challenges as summarized below:

- Poor and Inadequate policy, legal, and institutional frameworks: There is often weak regulation within the FBOs which lead to compromised governance issues.

- Governance and financial management problems: Weak leadership and institutional capacity, along with poor accounting and record-keeping practices, hindering cooperative development. In some cases, decision making leadership positions are either heavily dominated by men or women with generally very little participation of youth and PWDs.

- Lack of access to competitive markets: Failure to secure profitable markets for cooperative members and late sales payments usually discourage participation and investment commitment by farmers.

- Slow growth in membership and Shares: Potential members unable to buy shares in full while others literally failing to join due to high price of shares. Additionally, the FBOs fail to provide attractive services to its members due to lack of access to finance which makes them unable to buy produce from their members making the member farmers deciding to side sale. This makes it difficult for them to attract and retain members.

- Founder syndrome and prolonged stay in leadership positions: In some cases, especially for the milk bulking groups (MBGs) some of the leaders have the ego of the founder syndrome and have too much control, leading to a lack of democratic decision-making. In some cases, leaders overstaying in their positions and consolidate power whereby diminishing the required democratic principles of such farmer organizations.

- Dependency on external funding: Some of the FBOs are not well-established and rely heavily on external funding and technical assistance, which may lead to unsustainability in the long term.

- Reports and schedule of deliverables

The consultant is expected to deliver the following listed deliverables:

6.1 Broader deliverables

- Inception report (digital and hard copies of the assignment. The inception report should cover the methodologies and work plan and must be submitted to TRADE Programme at the latest 3 weeks after signing individual BC contracts).

- Rapid assessment report and coaching plans: To be submitted within three weeks after commencement of the assignment. The coaching plan should clearly have the indicators and targets agreeable by the FBOs.

- Interim / monthly reports: This should cover progress made as of that time of reporting. It is expected that these reports will include models, diagrams, photographs, contact list of training participants and other stakeholders present during trainings.

- Final reports: To cover all activities implemented in the assignment. To be submitted in electronic version including narrative, tables, etc using the recommended templates that will be provided to Business Coaches. All training modules will also be annexed to the report.

6.2 Specific Deliverables

- Improved Governance and Leadership: The governance and leadership of the FBOs should be improved focusing on the improvement and adherence to by-law stipulations of annual general meetings (AGMs), term limits as opposed to open term arrangements, structure and composition which must also consider compliance to women and youth representation thresholds of (40% W and 30 % Y).

- Improved Services Provision: The BC should handhold the FBOs to enhance the improvement of services provided to their members by measurable changes to achieve increased support for members in access to inputs and other resources, FBOs being able to also provide market services for their members.

- Increased Financial Management capabilities: The FBOs to improve financial management capabilities by ensuring that they are able to develop annual budgets, develop cash flows, internal control policies, financial reports in the format that can be clearly understood by the entire membership, etc.

- Share and membership growth: The BC must support the FBOs to sustainably increase their membership and capital by ensuring that all the members buy shares.

- Increased volumes of commodity aggregated: The BC to ensure that the FBOs are supported to, in a participatory manner, come up with attractive strategies that must enhance an significant increase in volumes of produce aggregated.

- Increased opportunities to access finance: The BC should support the FBO to develop a competitive business plan to be able to apply for ACIF matching grant or access to finance through other grant windows or available cheaper loans opportunities.

- Develop a profitable equipment hire scheme: The BC should support the FBOs to, where applicable, develop a profitable equipment hire scheme particularly targeting those FBOs which have such equipment as tractors, threshers, shellers and such related equipment.

- Reporting formats

TRADE Programme will supply monthly and end of assignment report formats as well as a template for a coaching plan to the business coaches which will be annexes to the business coaching assignment contract agreement. The reports will be submitted electronically using the email which will be indicated in the contract agreement. Where necessary, approved and signed hard copies of the reports will also be submitted in copies of three.

- Qualifications and experience required

The BCs will be required to be of relevant expertise knowledge, skills and experience to support and handhold the FBOs to fully commercialise their enterprises.

  - Qualifications and experience required

    - Academic Qualifications

The individual consultants should have the following:

      - At least a Bachelors’ Degree in Agribusiness, Agriculture enterprise Development, Agricultural Economics, Development Economics, Economics, Business Administration, Development Studies, Agronomy, Livestock, community development and other related fields.

  - General professional experience

A minimum of 3 years’ experience in and knowledge of:

    - Adult learning and participatory training methodologies (Indicate the approaches in the expression of interest (EoI) document)

    - Value Chain Development (Indicate in CV and provide a list of similar assignments)

    - DS analysis and development (Indicate in CV and provide a list of similar assignments, where possible attach certification)

    - Commodity marketing, value addition and processing as well as product certification (Indicate in EoI a list of similar interventions with other FBOs).

    - Good communication skills

    - Experience of previous business coaching for FBOs :

- Provide proof of at least 1 similar assignment carried out in the last three to five years.

- Attach copies of title and signature pages of contracts of similar assignments.

- Attach Business Coaching Certification

    - Experience in mainstreaming crosscutting issues (gender, environment and natural resources management, nutrition, youth and persons with disability inclusion) (Demonstrate in EoI proven experience in similar interventions).

  - Specific professional experience

Knowledge and experience in one or more of the following specific approaches

- Framer Organisation Business Training and Coaching Cycle (FO cycle) (attach certification),

- Start and improve your business (SIYB) (Attach certification)

- Small and Medium Enterprise (SME) Business Training and Coaching Loop (SME Loop) (Attach certification)

- Smallholder Empowerment and Promotion (SHEP) Approach (Indicate proven experience in the CV or expression of interest document